## Training Plan Workgroup
STAFF PERFORMANCE APPRAISAL PROJECT TRAINING PLAN TEMPLATE
*Assumes fiscal year implementation and assumes will apply only to 99 employees excluding Health Sciences
Proposed Training Needed | VC Area | Method/Format of Training | Timing of Training | Group responsible for creation | Group responsible for delivery | Estimated number of employees
Ex: Create an updated guide for completing staff performance appraisals. | All | Blink/PDF | Publish no later than April 1, 2016 | Employee Relations | Employee Relations | Unknown
Training on standardized definitions (i.e. POC) | All | Classroom, Webinar, Blink | TBD | Primary- SED Secondary- ER, OP, OSI, EDI, Compensation, VC HR Contacts | Primary- Employee Relations Secondary- SED, VC HR, OSI | ~3700 99 employees
Reference guide of standardized definitions | All | Blink/PDF, pop-up of definitions in online forms | TBD | Primary- SED Secondary- ER, OP, OSI, EDI, Compensation, VC HR Contacts | Primary- Employee Relations Secondary- SED | ~3700 99 employees
Supervisor module on "How to evaluate psychological rater biases" | All | Blink, e-learning, Instructor Led Training | TBD | Primary- SED Secondary- ER, OP, OSI, EDI, Compensation, VC HR Contacts | Primary- Employee Relations Secondary- SED | ~3700 99 employees
How to write a performance appraisal form | All | Blink, e-learning, Instructor Led Training | TBD | Primary- SED Secondary- ER, OP, OSI, EDI, Compensation, VC HR Contacts | Primary- Employee Relations Secondary- SED | ~3700 99 employees
What is the form? Define Terms | All | Blink, e-learning, Instructor Led Training | TBD | Primary- SED Secondary- ER, OP, OSI, EDI, Compensation, VC HR Contacts | Primary- Employee Relations Secondary- SED | ~3700 99 employees
FAQ's for supervisors | All | Blink, e-learning, Instructor Led Training | TBD | Primary- SED Secondary- ER, OP, OSI, EDI, Compensation, VC HR Contacts | Primary- Employee Relations Secondary- SED | ~3700 99 employees
FAQ's for employees | All | Blink, e-learning, Instructor Led Training | TBD | Primary- SED Secondary- ER, OP, OSI, EDI, Compensation, VC HR Contacts | Primary- Employee Relations Secondary- SED | ~3700 99 employees
How to have staff performance appraisal conversations | All | Blink, e-learning, Instructor Led Training | TBD | Primary- SED Secondary- ER, OP, OSI, EDI, Compensation, VC HR Contacts | Primary- Employee Relations Secondary- SED | ~3700 99 employees
How to have difficult conversations | All | Blink, e-learning, Instructor Led Training | TBD | Primary- SED Secondary- ER, OP, OSI, EDI, Compensation, VC HR Contacts | Primary- Employee Relations Secondary- SED | ~3700 99 employees
How to converse | All | Blink, e-learning, Instructor Led Training | TBD | Primary- SED Secondary- ER, OP, OSI, EDI, Compensation, VC HR Contacts | Primary- Employee Relations Secondary- SED | ~3700 99 employees
How to do quarterly 1:1's | All | Blink, e-learning, Instructor Led Training | TBD | Primary- SED Secondary- ER, OP, OSI, EDI, Compensation, VC HR Contacts | Primary- Employee Relations Secondary- SED | ~3700 99 employees
How to give and receive feedback | All | Blink, e-learning, Instructor Led Training | TBD | Primary- SED Secondary- ER, OP, OSI, EDI, Compensation, VC HR Contacts | Primary- Employee Relations Secondary- SED | ~3700 99 employees
How to develop effective performance goals | All | Blink, e-learning, Instructor Led Training | TBD | Primary- SED Secondary- ER, OP, OSI, EDI, Compensation, VC HR Contacts | Primary- Employee Relations Secondary- SED | ~3700 99 employees
How to respond as an employee to your supervisor's appraisal | All | Blink, e-learning, Instructor Led Training | TBD | Primary- SED Secondary- ER, OP, OSI, EDI, Compensation, VC HR Contacts | Primary- Employee Relations Secondary- SED | ~3700 99 employees
Train through a variety of mediums (webinars, classroom, handouts, faculty specific training) | All | Blink, e-learning, Instructor Led Training | TBD | Primary- SED Secondary- ER, OP, OSI, EDI, Compensation, VC HR Contacts | Primary- Employee Relations Secondary- SED | ~3700 99 employees
Guidelines for various appraisal structures (in-person, best practices, faculty specific) | All | Blink, e-learning, Instructor Led Training | TBD | Primary- SED Secondary- ER, OP, OSI, EDI, Compensation, VC HR Contacts | Primary- Employee Relations Secondary- SED | ~3700 99 employees
Train the trainers so each VC area has sufficient amount of trainers available | All | Blink, e-learning, Instructor Led Training | TBD | Primary- SED Secondary- ER, OP, OSI, EDI, Compensation, VC HR Contacts | Primary- Employee Relations Secondary- SED | ~3700 99 employees
Develop interactive training | All | Blink, e-learning, Instructor Led Training | TBD | Primary- SED Secondary- ER, OP, OSI, EDI, Compensation, VC HR Contacts | Primary- Employee Relations Secondary- SED | ~3700 99 employees
Coordination of all training efforts | All | Blink, e-learning, Instructor Led Training | TBD | Primary- SED Secondary- ER, OP, OSI, EDI, Compensation, VC HR Contacts | Primary- Employee Relations Secondary- SED | ~3700 99 employees
FAQ's for Academic Appraisals | All | Blink, e-learning, Instructor Led Training | TBD | Primary- SED Secondary- ER, OP, OSI, EDI, Compensation, VC HR Contacts | Primary- Employee Relations Secondary- SED | ~3700 99 employees
Unconscious bias training | All | Blink, e-learning, Instructor Led Training | TBD | Primary- SED Secondary- ER, OP, OSI, EDI, Compensation, VC HR Contacts | Primary- Employee Relations Secondary- SED | ~3700 99 employees
Train on the Represented vs. Non Represented Appraisals (by contract as appropriate) | All | Blink, e-learning, Instructor Led Training |  | Primary- SED Secondary- ER, OP, OSI, EDI, Compensation, VC HR Contacts | Primary- Employee Relations Secondary- SED | ~3700 99 employees